## UAT Tracker
# | Feedback Date | Priority | Dashboard Tab | Feedback | Sheet in this file to Refer | Person Responsible | Status | Completion Date
1 | 2026-09-17 | High | Quarterly Data Tabs | On top of the tab, "Previous Quarter" to be renamed as "QoQ", "Previous Year Same Quarter" to be renamed as "YoY" | - | Power BI Team | Completed
2 | 2026-09-17 | High | All Tabs | Default data should be of latest available period (e.g. latest quarter in case of quarterly data available). Currently it is showing FY26 as the default even where Q1FY27 data is available. | 2 | Power BI Team | Completed |  | Done
3 | 2026-09-17 | High | Valuations & Returns | P/B to be mapped from "Enterprise Data and Ratios" Excel file - not to be calculated. Data not ingested properly. | 3 | Both Data Engineering and Power BI Team | Not Started
4 | 2026-09-17 | High | Quarterly Data Tabs | Q1FY27 is not available in the drop down. | 4 | Power BI Team | Completed |  | Done
5 | 2026-09-17 | High | Overview | PAT for DRL - forward numbers were always available in columns BA and BB (see yellow cells in screenshots iin Tab "5") but are shown as NA in the dashaboard. Data has not been properly ingested/Old offline files have been used. | 5 | Both Data Engineering and Power BI Team | Not Started
6 | 2026-09-17 | High | Overview | Consensus Estimates Table in Overview to also be colour coded | 6 | Power BI Team | Completed |  | Done
7 | 2026-09-21 | High | Valuations & Returns | Consensus Estimates Table in Valuations & Returns Tab data were always available in columns AA and AB - not populated due to data ingestion issue again | 7 | Both Data Engineering and Power BI Team | Not Started
8 | 2026-09-21 | High | Quarterly Data Tabs | I understand current logic is annual data is summation of quarterly data. Logic to be built if annual data is "NA", to check if fiscal year data is available. E.g. Mankind in FY21. | 8 | Power BI Team | Not Started
9 | 2026-09-21 | High | All Tabs | Separate file for real time data like Share Price, Market Cap including Dates | NA | Aishwarya | Completed
10 | 2026-09-21 | High | All Tabs | To add a caption for Consensus Estimates "Note: The table below always reflects estimates for the next two fiscal years relative to the last reported fiscal year, irrespective of the period selected above." | 6 | Power BI Team | Completed |  | Done
11 | 2026-09-21 | High | All Tabs | FY20 data needed so that growth for FY21 is not NA | NA | Aishwarya | Not Started
12 | 2026-09-21 | High | All Tabs | All data in tables to be centre aligned, currently left aligned. KPI tiles can be as is. | 6 | Power BI Team | Not Started
13 | 2026-09-21 | High | All Tabs | Colour coding to include DRL as well. Looks like DRL is not included as there is no highest/lowest colour on any DRL number. Eg. In Fy21 DRL's gross profit margin was the lowest but, the next lowest i.e. Aurobindo is highlighted. | 13 | Power BI Team | Completed |  | Done
14 | 2026-09-21 | High | Overview | Check gross margin for DRL and if it is like to like, since different codes were used. Else hard code from IND AS | NA | Aishwarya | Not Started
15 | 2026-09-21 | High | Overview | "DRL Market-Cap Rank Overall XX of 10" should be "DRL Market-Cap Rank Overall XX of 10*" with a footnote *Incl. Divi's and Laurus. | 15 | Power BI Team | Not Started
16 | 2026-09-21 | Medium | Quarterly Data Tabs | Add option to select multiple quarters for a "YTD" view | NA | Power BI Team | Not Started
17 | 2026-09-17 | High | All Tabs | Option to download to PDF or Excel | NA | Power BI Team | Not Started
18 | 2026-09-21 | High | Overview | P/E ratio, EV/EBITDA - highest green, lowest red | 18 | Power BI Team | Not Started
19 | 2026-09-21 | High | Overview | P/E ratio, P/B, EV/EBITDA, EV/Sales - highest green, lowest red | 19 | Power BI Team | Not Started
20 | 2026-09-21 | High | Valuations & Returns | All ratios in Valuation Multiples - highest green, lowest red | 20 | Power BI Team | Not Started
21 | 2026-09-21 | High | Valuations & Returns | Market Cap Ranks - Lowest green, highest red | 21 | Power BI Team | Not Started
22 | 2026-09-21 | High | Valuations & Returns | ROCE, ROE, ROIC and Dividend Payout Ratio should have % sign (e.g. ROCE %) | 22 | Power BI Team | Not Started
23 | 2026-09-21 | High | Valuations & Returns | Dividend per share should have one decimal like all other numbers (currently 2 decimals) | 22 | Power BI Team | Not Started
24 | 2026-09-21 | High | Valuations & Returns | Market Cap Rank (of 10) - currently says of 8 | 21 | Power BI Team | Not Started
25 | 2026-09-21 | High | Valuations & Returns | Foot note should say "Divi's and Laurus Labs are in top cos by market cap" | 21 | Power BI Team | Not Started
26 | 2026-09-21 | High | Overview | Annual data points not relevant to quarters like ROCE are erroneously appearing when quarter is selected. Code to be checked. See screenshot for Q2FY26. | 26 | Power BI Team | Not Started
27 | 2026-09-21 | High | All Tabs | Monitoring needs to be enabled to check if data is getting refreshed and pulled into GBQ correctly. | NA | Data Engineering Team | Not Started
28 | 2026-09-21 | High | Valuations & Returns | P/E ratio, P/B, EV/EBITDA, EV/Sales should all have (x) as a suffix. E.g. P/E (x) | 19 | Power BI Team | Not Started
29 | 2026-09-21 | High | All Tabs | All tables should have the same column sizes | 29 | Power BI Team | Not Started
30 | 2026-09-21 | High | Trend Analysis | KPI Tiles for each Company should show Growth in case of Revenues, Margins in case of EBITDA, PAT instead of the absolute amounts. | 30 | Power BI Team | Not Started |  | CR
31 | 2026-09-21 | High | Trend Analysis | Metrics such as Share Price, Market Capitalisation, ROCE, Gross Profit Margin, P/E, EV/EBITDA to be added | 31 | Power BI Team | Completed
32 | 2026-09-22 | High | Trend Analysis | Growth Numbers are not visible on the purple background. | 32 | Power BI Team | Completed
33 | 2026-09-22 | High | Trend Analysis | Legend for purple shows the metric name e.g "Revenues" which is incorrect. All the bars are the same metric, not just the purple bar. Please delete this legend | 32 | Power BI Team | Completed
34 | 2026-09-22 | High | Trend Analysis | Add option to select multiple companies for a single metric. Currently only one at a time or all are possible. | 34 | Power BI Team | Completed
35 | 2026-09-22 | High | Trend Analysis | Add option to select quarters as well as years for a single company (trend over time). Currently only one year at a time. | 34 | Power BI Team | Not Started |  | Design needed
36 | 2026-09-22 | High | Trend Analysis | When multiple years are selected, the tiles above can include CAGR for revenue growth and average for others like margins. | 30 | Power BI Team | Not Started |  | CR
37 | 2026-09-22 | High | Trend Analysis | See how the drop downs can be placed. Year is on top and company and metric is below. | 34 | Power BI Team | Not Started
38 | 2026-09-23 | High | Revenue and Growth | Rename this tab as "Region Wise Revenues" | 38 | Power BI Team | Not Started
39 | 2026-09-23 | High | Revenue and Growth | When FY27 is selected in drop down, Q1FY27 numbers are visible. It should show NA. | 38 | Power BI Team | Not Started
40 | 2026-09-23 | High | Revenue and Growth | Header of the 1st table should be "Region Wise Revenues (₹ Cr) ¦ % of Total Revenues". Currently "Region Wise Revenue (₹ Cr) ¦ % Total Revenue" | 38 | Power BI Team | Not Started
41 | 2026-09-23 | High | All Tabs | Caption of Consensus Estimates should be below the heading and not above it. | 41 | Power BI Team | Not Started
42 | 2026-09-23 | High | Overview | When FY27 is selected in drop down, Q1FY27 numbers are visible. It should show NA. - new comment on old tabs based on new changes implemented to resolve #4 above. | 42 | Power BI Team | Not Started
43 | 2026-09-23 | High | Cost Structure and EBITDA | Drop Down on Left should also have DRL, so that DRL to DRL comparison across years can happen | 43 | Power BI Team | Not Started
44 | 2026-09-23 | High | Cost Structure and EBITDA | Caption says Selling and Marketing is available for Annual Data but is not mapped. Data is NA. | 44 | Power BI Team | Not Started
45 | 2026-09-23 | High | Revenue and Growth | Consensus Table should also have totals (Number to be taken from Income Statement Tab). All individual regions should add to Total. Difference if any should be captured as "Adjustment" similar to the 1st table in the tab. | 41 | Power BI Team | Not Started
46 | 2026-09-23 | High | Leverage & Cash Flow | All units like (x) should be in the 1st column and not with the number for consistency across tabs | 46 | Power BI Team | Not Started
47 | 2026-09-23 | High | Overview | All units like Rs. Cr, (x) should be in the header and not with the number for consistency across tabs | 47 | Power BI Team | Not Started |  | CR
48 | 2026-09-23 | High | Revenue and Growth | All units like % should be in the 1st column and not with the number for consistency across tabs | 48 | Power BI Team | Not Started
49 | 2026-09-23 | High | Valuations & Returns | All units like Rs. (x) should be in the header and not with the number for consistency across tabs | 49 | Power BI Team | Not Started
50 | 2026-09-23 | High | Leverage & Cash Flow | All units like Rs. (x) should be in the header and not with the number for consistency across tabs | 50 | Power BI Team | Not Started
51 | 2026-09-23 | High | Leverage & Cash Flow | All units like Rs. Cr, (x) should be in the header and not with the number for consistency across tabs | 51 | Power BI Team | Not Started
52 | 2026-09-23 | High | Leverage & Cash Flow | Rename CAPEX as "Capital Expenditure (Rs. Cr.) | 51 | Power BI Team | Not Started
53 | 2026-09-23 | High | All Tabs | Add "1 Year Forward" and "2 Year Forward" in all tabs in all base files in 1 row above the header | NA | Aishwarya | Completed
54 | 2026-09-23 | High | All Tabs | Consensus Numbers in many tabs not flowing through. Should flow through after #53 is completed | NA | Power BI Team | Not Started
55 | 2026-09-23 | High | Overview | To confirm source of data for P/E, Market Cap etc. when any quarter is selected. This data should only be available for Annual section or "As per Last Close Price". | 55 | Power BI Team | Not Started
56 | 2026-09-23 | High | Overview | Drop Down Option to be added "As per Last Close Price" along with Quarter and Year and data from the file shared as on 23rd September (Daily Data File Name) to be mapped to P/E, EV/EBITDA, Market Cap. All other parameters will be greyed out. | 56 | Both Data Engineering and Power BI Team | Not Started
57 | 2026-09-23 | High | Valuations & Returns | Drop Down Option to be added "As per Last Close Price" before the latest available year and data from the file shared as on 23rd September (Daily Data File Name) to be mapped to available data. All other parameters will be greyed out. | 57 | Both Data Engineering and Power BI Team | Not Started
58 | 2026-09-23 | High | Valuations & Returns | To confirm source of data when FY27 is selected as there is no Annual Data for this year. Is this Current Data? | 57 | Both Data Engineering and Power BI Team | Not Started
59 | 2026-09-23 | High | NA | To schedule all files except "Daily Data" for once in 2 weeks, on Mondays at 9am. Daily Data to be scheduled for refresh every week day (Monday to Friday) at 9am. If System is not available, to retry at 11am. If still not available, alert to be schedules to Data Engineering, Shaunak and Aishwarya. | NA | Data Engineering Team | Not Started

## List (hidden)
Completed
Ongoing
Not Started